## Issue-list
#Item no | Desc | Type | Priority | owner | Effort | Given ETA | Actual ETA | Desc
1 | Sonar | Quilaty check | 1 | Manoj/Vij |  | 2023-07-19 |  | done, Some of the team member able to generate Sonar report but not all
2 | Code review guideline | Quilaty check | 2 | Vijay |  | 2023-07-18 | 2023-07-18 | Done
3 | Microservice Architecture | Architecute | 3 | Manoj/Vij |  | 2023-07-21 |  | Request date 8-Aug
4 | Trivy/Harbor | Security check | 4 | Manoj/VIJ |  | 2023-07-25 |  | Application errors got fixed and working on Image errors
5 | High availability | NFR | 5 | Vij/SPG |  | 2023-07-21
6 | 12/15 factor | Best Practice | 8 | Manoj/Vij
7 | Microservice best practice | Best Practice | 9 | Manoj/Vij
8 | API guidelines | Best Practice | 6 | Manoj/Vij |  | 2023-07-18 | 2023-07-18
9 | DB-design | Design | 7 | Manoj/Vij |  | 2023-07-21
10 | Bar-code | POC | 1 | Rajeev |  | 2023-07-21 |  | Error while creating Kafka cluster. working with infra team to fix
11 | API http method/nameing | Best Practice |  | Dhananjay
12 | Logs / ELK | Monitoring | 10 | Vij/Sujatha
| Quilaty check |  | Manoj
| ARchitecture |  | Manoj
| Security | Trivy Harbor | Manoj
| Best PRactices |  | Manoj
| Monitoring | Logs / ELK | Manoj
| BAR Code |  | Rajeev V | Functional.
Story Links
NFR : Best Practices Adaptation and Implementation
https://tdem.atlassian.net/browse/TPEX-2020
1 | https://tdem.atlassian.net/browse/TPEX-2043
NFR : Quality check Guidelines and Implementation.
2 | https://tdem.atlassian.net/browse/TPEX-2010
NFR : Architecture Related Activities
3 | https://tdem.atlassian.net/browse/TPEX-2021
NFR : Monitoring Logs
4 | https://tdem.atlassian.net/browse/TPEX-2022
NFR : Security related : Development and Implementation Activities.
5 | https://tdem.atlassian.net/browse/TPEX-2023
BAR Code POC & Implementation
6 | https://tdem.atlassian.net/browse/TPEX-2024
TPEX-2022 NFR : Authentication and Authorization
7 | https://tdem.atlassian.net/browse/TPEX-2165
8 | Sprint Batch framework
https://tdem.atlassian.net/browse/TPEX-2164

## Sonar
Step-1 | Sonarlint plugin install in intellj and integrate Sonarqube server | Step -1
Stepes to install SonarLint plugin Intellj and integrate with SonarQube server
Step-2 | Install SonarQube server locally on developer box and integrate with SonarLint
|  | Step - 2 | Install SonarQube server in local and integrate

## CodeReview-guideline
S. No. | Items | Examples
1.1 | Naming Convensions
| 1. Class names should be in Pascal Case and should reflect the purpose or functionality of the class. 2.Method and variable names should be in camelCase and should be descriptive. 3.Constant names should be in uppercase with underscores separating words. or use enums 4.Package names should be in lowercase and follow the reverse domain name convention (e.g., com.example.project). | 1. Class names should be in Pascal Case and reflect the purpose or functionality of the class: public class Car { // Starting letter capital is called Pascal case // Class implementation } 2. Method and variable names should be in camelCase and be descriptive: public class Car { private String manufacturer; public void startEngine() { // camelCase // Method implementation } public void accelerate(int speed) { // Method implementation } public String getManufacturer() { //camelCase return manufacturer; } } 3. Constant names should be in uppercase with underscores separating words: public class Car { public static final int MAX_SPEED = 200; public static final String DEFAULT_COLOR = "black"; } or enum public enum HttpStatus { OK(200), NOT_FOUND(404), INTERNAL_SERVER_ERROR(500); private final int code; HttpStatus(int code) { this.code = code; } public int getCode() { return code; } } // Usage: HttpStatus status = HttpStatus.NOT_FOUND; System.out.println("HTTP status code: " + status.getCode()); // Output: HTTP status code: 404 4. Package names should be in lowercase and follow the reverse domain name convention: package com.example.project; public class Car { // Class implementation } These naming conventions help improve code readability and maintainability.
1.2 | Indentation and Formatting
| 1.Use a consistent indentation style, such as 4 spaces or a tab. 2.Use braces ({}) for control structures (if statements, loops, etc.) even for single statements. 3.Constant names should be in uppercase with underscores separating words. | 1. Use a consistent indentation style, such as 4 spaces or a tab: public class ExampleClass { public static void main(String[] args) { int number = 10; if (number > 5) { System.out.println("Number is greater than 5."); } else { System.out.println("Number is less than or equal to 5."); } } } 2. Use braces ({}) for control structures (if statements, loops, etc.) even for single statements: public class ExampleClass { public static void main(String[] args) { int number = 10; if (number > 5) { System.out.println("Number is greater than 5."); System.out.println("This is another statement."); } else { System.out.println("Number is less than or equal to 5."); System.out.println("This is another statement."); } } } 3. Constant names should be in uppercase with underscores separating words: public class ExampleClass { public static final int MAX_VALUE = 100; public static final String DEFAULT_COLOR = "black"; public static void main(String[] args) { System.out.println(MAX_VALUE); System.out.println(DEFAULT_COLOR); } }
1.3 | Comments and Documentation
| 1.Use comments to explain the purpose, functionality, and logic of complex code sections. 2.Document classes, methods, and significant variables using Javadoc comments. 3.Update comments and documentation when code changes to keep them accurate and up to date. 4.Use swagger for understand contract input/output payload | 1. Use comments to explain the purpose, functionality, and logic of complex code sections: public class ExampleClass { public static void main(String[] args) { int number = 10; // Check if the number is greater than 5 if (number > 5) { System.out.println("Number is greater than 5."); } else { System.out.println("Number is less than or equal to 5."); } } } 2. Document classes, methods, and significant variables using Javadoc comments: /** * This is an example class that demonstrates Javadoc comments. */ public class ExampleClass { /** * This is the main method which is the entry point of the program. * * @param args The command line arguments. */ public static void main(String[] args) { int number = 10; // Check if the number is greater than 5 if (number > 5) { System.out.println("Number is greater than 5."); } else { System.out.println("Number is less than or equal to 5."); } } } 3. Update comments and documentation when code changes to keep them accurate and up to date. It's important to maintain documentation alongside code changes to ensure consistency and accuracy. 4. Use Swagger for understanding contract input/output payload. Swagger is a popular tool for documenting and describing APIs. It provides a structured way to define the input and output payloads, endpoints, and other information related to the API contract. By using Swagger, developers and users can easily understand the API structure, request/response formats, and available endpoint
1.4 | Error/Exception Handling
| 1.Use appropriate exception handling mechanisms (try-catch blocks) for expected and exceptional conditions. 2.Catch specific exceptions rather than using a general catch-all statement. 3.Log exceptions or error messages with meaningful information for troubleshooting and debugging. 4.All exceptions should be properly caught, logged, or propagated as appropriate. 5.Empty catch blocks should be avoided. | 1. Use appropriate exception handling mechanisms (try-catch blocks) for expected and exceptional conditions: try { // Code that may throw an exception } catch (ExceptionType1 exception1) { // Handling for ExceptionType1 } catch (ExceptionType2 exception2) { // Handling for ExceptionType2 } 2. Catch specific exceptions rather than using a general catch-all statement: try { // Code that may throw exceptions } catch (IOException ex) { // Handling for IOException } catch (SQLException ex) { // Handling for SQLException } 3. Log exceptions or error messages with meaningful information for troubleshooting and debugging: try { // Code that may throw exceptions } catch (IOException ex) { // Handling for IOException logger.error("An I/O error occurred: " + ex.getMessage()); } catch (SQLException ex) { // Handling for SQLException logger.error("A SQL error occurred: " + ex.getMessage()); } 4. All exceptions should be properly caught, logged, or propagated as appropriate. It's important to handle exceptions to prevent unexpected program termination and to ensure proper error handling. 5. Empty catch blocks should be avoided. Catching an exception without any handling code makes it difficult to identify and debug issues. It's best to handle or log exceptions appropriately to provide meaningful feedback or take necessary actions. Following these guidelines helps ensure that exceptions are handled properly, logged for debugging purposes, and that the code maintains proper control flow even in the presence of exceptions.
1.5 | Java Language Features
| 1.Use meaningful and self-explanatory variable and method names to enhance code readability. 2.Avoid using magic numbers or hard-coded values, use constants or configuration files instead. 3.Utilize Java 8 features such as lambdas, functional interfaces, and streams where appropriate and beneficial. | 1. Use meaningful and self-explanatory variable and method names to enhance code readability: public class ExampleClass { private int numberOfStudents; public void calculateAverageGrade() { // Method implementation } public String getFullName() { // Method implementation } } 2. Avoid using magic numbers or hard-coded values, use constants or configuration files instead: public class ExampleClass { private static final int MAX_SCORE = 100; private static final int MIN_SCORE = 0; public void calculateGrade(int score) { if (score > MAX_SCORE) { System.out.println("Invalid score. Maximum allowed score is " + MAX_SCORE); } else if (score < MIN_SCORE) { System.out.println("Invalid score. Minimum allowed score is " + MIN_SCORE); } else { // Grade calculation logic } } } 3. Utilize Java 8 features such as lambdas, functional interfaces, and streams where appropriate and beneficial: import java.util.Arrays; import java.util.List; import java.util.stream.Collectors; public class ExampleClass { public static void main(String[] args) { List<String> fruits = Arrays.asList("apple", "banana", "orange", "kiwi"); // Example using lambda and stream List<String> filteredFruits = fruits.stream() .filter(fruit -> fruit.length() > 5) .collect(Collectors.toList()); System.out.println(filteredFruits); // Output: [banana, orange] } }
1.7 | Testing and Quality Assurance
| 1.Write unit tests to cover critical components, functionalities, and edge cases. 2.Use testing frameworks like JUnit or Mockito for writing and running tests. | In this example, the `Calculator` class depends on a `MathOperations` interface, which is mocked using Mockito. The `@BeforeEach` method initializes the mock and creates an instance of the `Calculator` class. import org.junit.jupiter.api.Assertions; import org.junit.jupiter.api.BeforeEach; import org.junit.jupiter.api.Test; import org.mockito.Mock; import org.mockito.MockitoAnnotations; import static org.mockito.Mockito.*; public class CalculatorTest { private Calculator calculator; @Mock private MathOperations mathOperationsMock; @BeforeEach public void setUp() { MockitoAnnotations.openMocks(this); calculator = new Calculator(mathOperationsMock); } @Test public void testAddition() { when(mathOperationsMock.add(5, 3)).thenReturn(8); int result = calculator.add(5, 3); Assertions.assertEquals(8, result); verify(mathOperationsMock).add(5, 3); } @Test public void testSubtraction() { when(mathOperationsMock.subtract(7, 4)).thenReturn(3); int result = calculator.subtract(7, 4); Assertions.assertEquals(3, result); verify(mathOperationsMock).subtract(7, 4); } @Test public void testMultiplication() { when(mathOperationsMock.multiply(2, 6)).thenReturn(12); int result = calculator.multiply(2, 6); Assertions.assertEquals(12, result); verify(mathOperationsMock).multiply(2, 6); } @Test public void testDivision() { when(mathOperationsMock.divide(10, 2)).thenReturn(5); int result = calculator.divide(10, 2); Assertions.assertEquals(5, result); verify(mathOperationsMock).divide(10, 2); } @Test public void testDivisionByZero() { when(mathOperationsMock.divide(10, 0)).thenThrow(ArithmeticException.class); Assertions.assertThrows(ArithmeticException.class, () -> { calculator.divide(10, 0); }); verify(mathOperationsMock).divide(10, 0); } }
1.8 | Dependency Management
| 1.Use a dependency management tool like Maven or Gradle to manage project dependencies. 2.Declare dependencies with appropriate versions and scopes in the build configuration file (pom.xml or build.gradle). 3.Regularly update and review the dependencies to ensure they are up to date and secure. | 1.Choose a Dependency Management Tool: Maven and Gradle are popular dependency management tools. Choose the one that best suits your project's requirements and set it up in your development environment. 2.Create Build Configuration File: In Maven, the build configuration file is `pom.xml`, while in Gradle, it is `build.gradle`. These files define project configurations, including dependencies. 3.Declare Dependencies: Open the build configuration file and declare the dependencies your project requires. Specify the appropriate version and scope for each dependency. Here's an example of how you can declare a dependency in Maven and Gradle: Maven (pom.xml): <dependencies> <dependency> <groupId>org.example</groupId> <artifactId>example-library</artifactId> <version>1.0.0</version> <scope>compile</scope> </dependency> </dependencies> ``` Gradle (build.gradle): dependencies { implementation 'org.example:example-library:1.0.0' } In these examples, `org.example` represents the group or organization that owns the library, `example-library` is the library's artifact ID, and `1.0.0` is the version number. The `compile` or `implementation` scope indicates that this dependency is required for compilation and runtime. 4. Update and Review Dependencies:** Regularly update and review your project's dependencies to ensure they are up to date and secure. Outdated dependencies may contain security vulnerabilities or compatibility issues. Use the dependency management tool's commands or plugins to update dependencies automatically or manually review and update them as needed.
1.9 | Version Control and Collaboration
| 1.Utilize a version control system (such as Git) to manage code changes and collaborate with other developers. 2.Follow best practices for branching, commit messages, and pull requests. 3.Avoid committing incomplete or non-working code to the main branch. | 1. Set up Git: Install Git on your local machine and create a new repository for your project. You can initialize a Git repository in your project directory using the command `git init`. 2. Create Branches: Follow best practices for branching to organize your code changes effectively. Create separate branches for new features, bug fixes, or any other significant changes. This helps isolate changes and allows for parallel development. Use meaningful and descriptive branch names to convey the purpose of the changes. git branch feature/add-login git checkout feature/add-login 3. Commit Changes: Make granular and logical commits that represent coherent changes. Committing frequently helps in tracking and understanding the progress of your work. Write clear and descriptive commit messages to explain the purpose of the changes. Use the following command to stage and commit changes: git add . git commit -m "Add login feature" 4. Collaborate with Pull Requests:When you complete a feature or fix, push your branch to a central repository and create a pull request (PR) to merge it into the main branch. Follow best practices for pull requests: - Provide a detailed description of the changes and their purpose. - Assign reviewers to ensure code quality and receive feedback. - Respond to comments and address any requested changes. - Perform code reviews on others' pull requests to maintain code quality and learn from each other. 5. Avoid Committing Incomplete or Non-Working Code:It's crucial to avoid committing incomplete or non-working code to the main branch. Only merge branches into the main branch when the code is tested, functioning correctly, and reviewed by peers. This ensures that the main branch remains stable and usable for all developers. If you're working on an experimental or incomplete feature, create a separate branch or use feature flags to isolate and hide the unfinished code from the main branch.
1.1 | Security and Data Protection
| 1.Safeguard sensitive information, such as passwords or API keys, by using appropriate encryption or secure storage mechanisms. 2.SQL queries should be parameterized or prepared statements should be used to prevent SQL injection. 3.User inputs should be properly validated and sanitized to prevent cross-site scripting (XSS) attacks. | 1. Safeguard Sensitive Information: Follow these practices to protect sensitive information: - Never store passwords or sensitive data in plain text. Use appropriate encryption mechanisms like bcrypt or Argon2 to securely hash passwords before storing them in a database. - Avoid hardcoding API keys, credentials, or any sensitive information directly in the code. Instead, use secure storage mechanisms such as environment variables, secret management tools, or configuration files with restricted access. - Regularly review and rotate your passwords and API keys to minimize the potential impact of a security breach. - Limit access to sensitive information on a "need-to-know" basis and follow the principle of least privilege. 2. Prevent SQL Injection: Protect your database from SQL injection attacks by following these guidelines: - Use parameterized queries or prepared statements provided by your database framework or ORM (Object-Relational Mapping) library. These mechanisms automatically handle escaping and sanitizing user input, preventing malicious SQL injection. - Avoid dynamically building SQL queries by concatenating user inputs. This makes your code vulnerable to SQL injection attacks. Always use parameterized queries or prepared statements to separate SQL code from user input. 3. Validate and Sanitize User Inputs:Proper validation and sanitization of user inputs help prevent cross-site scripting (XSS) attacks. Here's what you should do: - Validate user input on both the client and server sides. Perform checks to ensure that the input adheres to the expected format, length, and type. - Use server-side input validation as the primary defense mechanism. Client-side validation is useful for providing immediate feedback to users, but it can be bypassed, so always validate on the server-side. - Sanitize user input by removing or escaping any special characters that could be interpreted as HTML, JavaScript, or SQL code. Use appropriate sanitization functions provided by your programming language or framework.
1.11 | Unused Code
| 1.Unused private methods, fields, or local variables should be removed. 2.Unused method parameters should be eliminated. | 1. Remove Unused Private Methods, Fields, and Local Variables: - Private methods: If a method is not used anywhere within the class or its subclasses, it is likely safe to remove it. Removing unused private methods reduces clutter and improves code readability. Be sure to review the codebase and ensure that the method is truly unused before removing it. - Private fields: Similar to private methods, if a field is not used within the class or its subclasses, consider removing it. Unused fields consume memory and can lead to confusion for other developers working on the codebase. - Local variables: Local variables that are declared but not used within a method should be removed. Unused local variables make the code harder to read and understand. Removing them improves code clarity and reduces unnecessary clutter. 2. Eliminate Unused Method Parameters: - Unused method parameters can be a sign of code that has changed over time or incomplete refactoring. Review your code and eliminate any method parameters that are not used within the method body. - However, be cautious when removing parameters from public API methods, as it can break backward compatibility. If the method is part of a public API and the parameter is no longer needed, consider deprecating the method and introducing a new version without the unused parameter. - Before removing a parameter, ensure that it is not used indirectly through other method invocations or external dependencies. Changing method signatures should be done carefully to avoid introducing bugs or unexpected behavior.
1.12 | Code Duplication
| 1.Blocks of code that are identical or similar should be refactored into reusable methods or extracted as constants. | 1. Identify Duplicate or Similar Code Blocks: Carefully review your codebase to identify blocks of code that are identical or share significant similarities. Look for patterns, repeated logic, or sections that perform similar operations. 2. Extract Reusable Methods: Once you identify a code block that is repeated or has similar functionality, extract it into a separate method. Give the method a descriptive name that reflects its purpose. Pass any necessary parameters to the method and return values if needed. public void processUserData(String name, int age) { // Common code block validateUserData(name, age); saveUserData(name, age); sendNotification(name); } private void validateUserData(String name, int age) { // Validation logic } private void saveUserData(String name, int age) { // Save data logic } private void sendNotification(String name) { // Send notification logic } 3. Extract Constants If you have sections of code that use the same values repeatedly, consider extracting them as constants. This improves code readability and makes it easier to update values in the future. private static final int MAX_RETRY_ATTEMPTS = 3; private static final String DEFAULT_USER_ROLE = "user"; public void doSomething() { for (int i = 0; i < MAX_RETRY_ATTEMPTS; i++) { // Perform retry logic } // Use DEFAULT_USER_ROLE in multiple places } By extracting constants, you can easily modify the value in a single place if needed, and the change will propagate throughout the codebase. 4. Ensure Correctness and Testability: After refactoring the code, ensure that the extracted methods or constants are correct and do not introduce any unintended side effects. Update any references to the extracted code and test the modified code to ensure it behaves as expected.
1.13 | Null Pointer Dereference
| 1.Null checks should be performed before dereferencing variables or invoking methods on them to avoid NullPointerException. | 1. Perform Null Checks: - Before dereferencing a variable or accessing its methods or properties, check if it is null using an `if` statement or the ternary operator. - Example with an `if` statement: if (variable != null) { // Perform operations on the variable variable.method(); } - Example with the ternary operator: variable = (variable != null) ? variable.method() : defaultValue; 2. Handle Null Cases Appropriately: - If a null value is unexpected or indicates an error condition, consider throwing a custom exception or an appropriate built-in exception (e.g., `IllegalArgumentException`, `IllegalStateException`). - Example: if (variable == null) { throw new IllegalArgumentException("Variable cannot be null."); } - Alternatively, you can assign a default value or provide a fallback behavior when encountering null values. - Example with a default value: String value = (variable != null) ? variable.getValue() : "default"; - Example with fallback behavior: String value = (variable != null) ? variable.getValue() : performFallbackOperation(); 3. Follow Defensive Programming Practices: - Initialize variables with default or meaningful values to avoid null values whenever possible. - Avoid returning null values from methods unless it is a deliberate design choice and well-documented. - Use null-safe operators or utility methods provided by your programming language or libraries to handle null cases concisely and safely. - Example with the null-safe operator (Java 8+): String value = variable?.getValue(); ``` - Example with utility method (Java: Apache Commons Lang): String value = StringUtils.defaultIfNull(variable, "default");
1.14 | Code Complexity
| 1.Methods or classes with high cyclomatic complexity (too many branching paths) should be simplified or refactored. 2.Nested control structures should be reduced to improve code readability and maintainability. | 1. Simplify Methods or Classes with High Cyclomatic Complexity: - Cyclomatic complexity measures the number of linearly independent paths through a method or class. High complexity indicates increased code complexity, making it harder to understand, maintain, and test. - Identify methods or classes with high cyclomatic complexity using tools or by manually analyzing the code. Aim to reduce complexity to a manageable level. - Refactor complex methods or classes by breaking them down into smaller, more focused methods or classes. Each method or class should have a single responsibility, making it easier to understand and maintain. - Use control structures (such as if-else, switch-case) judiciously and avoid nesting them excessively. Extract complex conditions into separate methods with descriptive names to improve code readability. - Apply design patterns, such as the Strategy pattern or State pattern, to encapsulate complex logic and reduce cyclomatic complexity. 2. Reduce Nested Control Structures: - Excessive nesting of control structures (if-else, for, while, switch-case) can lead to code that is hard to read and understand. It can also make the code more error-prone and difficult to maintain. - Aim to reduce nested control structures by applying these techniques: - Use early returns or continue statements to exit a method or loop early when a condition is met. This avoids excessive nesting and improves code clarity. - Extract nested logic into separate methods or functions. This helps in breaking down complex logic and reduces the depth of nested control structures. - Use guard clauses or assertions to handle exceptional cases or edge conditions at the beginning of a method. This allows the main logic to be written with reduced nesting. - Consider refactoring deeply nested control structures into more readable constructs like switch statements, polymorphism, or functional programming techniques. - Keep in mind that reducing nested control structures improves code readability and maintainability, making it easier for other developers to understand and modify the code.
1.15 | Performance Optimization
| 1.Inefficient code constructs, such as redundant computations or unnecessary object creation, should be optimized. 2.Expensive operations, like database queries or I/O operations, should be minimized or optimized. | 1. Optimize Inefficient Code Constructs: - Identify and eliminate redundant computations or unnecessary object creations. Review your code and look for areas where the same computation is performed multiple times, or where objects are created unnecessarily. - Cache or store computed values instead of recomputing them repeatedly. This can be achieved by using memoization techniques or caching libraries. - Avoid unnecessary string concatenation in loops. Instead, use `StringBuilder` or similar constructs to efficiently build strings. - Replace expensive operations with more efficient alternatives. For example, use efficient algorithms or data structures when sorting, searching, or manipulating collections of data. - Profile and benchmark your code to identify performance bottlenecks and areas that require optimization. Use tools and techniques to measure the execution time of different parts of your code and focus on optimizing the critical sections. 2. Minimize or Optimize Expensive Operations: - Database queries: Minimize the number of database queries by using efficient query design techniques such as joins, appropriate indexing, and query optimization. Consider using caching mechanisms or denormalization strategies where appropriate to reduce database access. - I/O operations: Optimize I/O operations by reducing the number of read or write operations and optimizing data transfer. Use buffering mechanisms, batch operations, or asynchronous I/O when applicable. - Network operations: Minimize network round trips by optimizing network communication. Use techniques like connection pooling, request/response compression, and caching to reduce latency and bandwidth usage. - Heavy computations: Optimize computationally intensive operations by using more efficient algorithms or data structures. Consider parallelization or distributed computing techniques to leverage the power of multi-core processors or distributed systems. - Resource management: Ensure proper resource management by closing database connections, releasing file handles, and freeing up system resources promptly. Use try-with-resources or similar constructs to ensure proper cleanup even in case of exceptions.

## Architecture
Architecture | Desc | IS Approved status | ETA
4+1 view architecture | The 4+1 view architecture is a software architecture design approach that helps in organizing and documenting the various perspectives or views of a complex software system. It provides a structured way to describe the system's architecture by decomposing it into five different views, each addressing specific concerns. The "+1" in the 4+1 view architecture represents an additional view that acts as an integration point for the other views, providing a holistic perspective of the system. Here's a breakdown of the four views in the 4+1 view architecture: 1. Logical View: This view focuses on the functionality and behavior of the system from a functional or business perspective. It describes the system in terms of its modules, components, classes, and their interactions. The logical view is concerned with high-level concepts and relationships rather than implementation details. 2. Development View: The development view focuses on the software development process and addresses the organization of the system's source code and components. It deals with concerns such as modules, libraries, dependencies, and build processes. This view helps developers understand how the system can be constructed and maintained. 3. Process View: The process view emphasizes the system's runtime behavior and the interactions between its components and processes. It describes the dynamic aspects of the system, including concurrency, distribution, and performance considerations. This view is crucial for understanding system behavior under various execution scenarios. 4. Physical View: The physical view describes the system's deployment topology and the mapping of its components onto physical resources such as hardware, networks, and infrastructure. It addresses concerns such as scalability, availability, and performance optimization based on the physical environment. Additionally, the "+1" view is known as the Scenarios or Use Cases view. It provides concrete examples or scenarios that illustrate how the system interacts with its users and external entities. This view helps stakeholders understand the system's functionality in practical terms. By using the 4+1 view architecture, software architects can communicate and document the different aspects of a system's design, facilitating better understanding, collaboration, and decision-making among development teams and stakeholders.
Common Architecture diagram | 1 High-Level System Architecture Diagram: This diagram provides an overview of the system and its various components, including microservices, databases, external services, and communication channels. 2. Microservices Architecture Diagram: This diagram illustrates the individual microservices within the system, their boundaries, and the interactions between them. It helps to identify the services involved in the migration and their dependencies. 3. Infrastructure Architecture Diagram: This diagram depicts the cloud infrastructure components required for hosting and running the microservices. It includes details on virtual machines, containers, load balancers, and other cloud-specific services used in the migration. 4. Network Architecture Diagram: This diagram focuses on the networking aspects of the migration, including how the microservices communicate with each other and with external services. It highlights network boundaries, firewalls, and security measures. 5. Data Flow Diagram: This diagram showcases the flow of data between the microservices and external systems. It helps to identify data sources, transformation points, and data storage mechanisms within the system. 6. Service Discovery and Routing Diagram: This diagram illustrates the service discovery and routing mechanisms used in the microservices architecture. It can include technologies like API gateways, load balancers, and service registries. 7. Security Architecture Diagram: This diagram outlines the security measures implemented within the microservices architecture, including authentication, authorization, encryption, and access controls. 8. Scalability and Resilience Diagram: This diagram focuses on the scalability and resilience aspects of the microservices architecture. It highlights mechanisms such as horizontal scaling, auto-scaling, fault tolerance, and disaster recovery.
cloud platform diagram | 1 Containers: If you are using containerization technologies like Docker or Kubernetes, depict the containerized applications and their relationship to the underlying infrastructure. 2 Storage: Show the different storage services offered by the cloud provider, such as object storage (Amazon S3, Azure Blob Storage), block storage (Amazon EBS, Azure Disk Storage), or file storage (Amazon EFS, Azure Files). Represent any relevant data replication or backup mechanisms. 3 Networking: Illustrate the networking components of your cloud platform, including virtual networks, subnets, security groups, and load balancers. Highlight the communication channels between different components and any VPN or direct connect connections. 4 Managed Services: Cloud providers offer a range of managed services that abstract away the operational complexity. Include services like managed databases (Amazon RDS, Azure Database), serverless computing (AWS Lambda, Azure Functions), or messaging queues (Amazon SQS, Azure Service Bus). 5 Identity and Access Management (IAM): Showcase the IAM services provided by the cloud platform, representing user roles, access policies, and authentication mechanisms. Highlight any integration with external identity providers. 6 Monitoring and Logging: Depict the monitoring and logging tools or services you are using to collect metrics, monitor performance, and track logs. This can include services like Amazon CloudWatch, Azure Monitor, or third-party tools like Datadog or New Relic. 7 Security Services: Include any security-related services you are using, such as firewall configurations, encryption services, intrusion detection and prevention systems (IDS/IPS), or vulnerability scanning tools.

## NFR
High Availability
s no. |  | Wonership | Microservices Details | [7 empty] | s. no | Services | Replicas | Request per sec | user | service Load/trafic | Resource Utilisation | scalibility | response time & lettency | trafic Patter & pick
|  |  | S no. | Microservices list | No. of pods | CPU core | End Point | Deployment Status | API GTW
| High Availability in OpenShift |  | 1 | tpex-ui-pwa-react | 1 | 800 Mi |  | done
|  |  | 2 | tpex-invoice-service | 1 | 300 Mi |  | done
1 | Multiple Replicas :- Deploy multiple replicas of your application across different nodes or availability zones |  | 3 | tpex-admin-service | 1 | 300 Mi |  | done
|  |  | 4 | tpex-month-service | 1 | 300 Mi |  | done
2 | Node and Zone Affinity :- Use node and zone affinity rules to ensure that the replicas of your application are spread across different nodes and availability zones. This helps in distributing the workload and minimizing the impact of a single node or zone failure. | N/A | 5 | tpex-daily-service | 1 | 200 Mi |  | done
|  |  | 6 | tpex-invoice-batch | 1 | 300 Mi |  | done
3 | Auto Scaling :- Configure horizontal pod autoscaling (HPA) in OpenShift to automatically scale the number of replicas based on CPU utilization, memory usage, or custom metrics. |  | 7 | tpex-barcode-publisher | 1 | 200 Mi |  | done
4 | Load Balancing :- Use the OpenShift router or integrate with external load balancers to distribute requests evenly and avoid overloading a specific replica. | [8 empty] | Recovery point objective (RPO)
5 | Persistent Storage :- application requires persistent storage, leverage OpenShift's support for persistent volume claims (PVCs) and persistent volumes (PVs). By using storage replication or distributed file systems, you can ensure data availability even if a node or PV fails. | [8 empty] | Recovery time objective (RTO)
6 | Rolling Updates :- When deploying updates or new versions of your application, use OpenShift's rolling update strategy. This strategy replaces instances one by one, ensuring that your application remains available throughout the update process.
7 | Probes and Health Checks :- Implement liveness and readiness probes in your application containers to enable OpenShift to check their health.
8 | Monitoring and Alerting :- Set up monitoring and alerting systems to monitor the health and performance of your OpenShift cluster and applications.
9 | Disaster Recovery :- Plan for disaster recovery scenarios by implementing backup and restore procedures for your OpenShift cluster and applications. Regularly back up critical data and configurations, and test the restoration process to ensure data availability in case of a major outage.
10 | Multi-Cluster Deployments :- For higher availability and disaster recovery across different geographical regions, consider setting up multi-cluster deployments
High Availability in a Spring Boot application
1 | Load Balancing :- Set up a load balancer to distribute incoming requests across multiple instances of your Spring Boot application. This helps distribute the load and ensures that if one instance fails, the others can handle the requests. | customer
2 | Clustering :- Use a clustering solution to create a cluster of Spring Boot instances. This allows you to scale horizontally by adding more instances to the cluster. The cluster should be able to handle automatic failover in case one of the instances goes down. | Openshift /infra
3 | Database Replication:- If your application relies on a database, consider setting up database replication. This involves maintaining multiple copies of the database, typically with a master-slave configuration. Replication ensures that if the master database fails, one of the slave databases can take over seamlessly | Openshift
4 | Statelessness :- Design your application to be stateless as much as possible. Avoid storing session information or any other state on individual instances of your Spring Boot application. This allows any instance to handle any request, improving availability and scalability | Application
5 | Health Checks and Monitoring :- Implement health checks in your Spring Boot application to regularly monitor the status of each instance. Use tools like Spring Boot Actuator to expose health endpoints and integrate with monitoring systems. This enables proactive detection of any issues and allows you to take corrective measures quickly. | Application
6 | Automatic Scaling :- Utilize cloud platforms or container orchestration tools like Kubernetes to automatically scale the number of instances based on demand. This ensures that your application can handle varying loads without manual intervention. | Openshift /BA/App
7 | Fault Tolerance :- Implement mechanisms such as circuit breakers, retry policies, and fallback mechanisms to handle failures gracefully. Libraries like Netflix Hystrix or resilience4j can help you implement these patterns in your Spring Boot application. | Application
8 | Continuous Deployment :- Embrace continuous deployment practices to roll out updates and bug fixes with minimal downtime. Techniques like blue-green deployments or canary releases can help ensure high availability during the deployment process. | Openshift/ app
9 | Disaster Recovery :- Set up a disaster recovery plan that includes regular backups, off-site storage, and clear procedures for restoring your application in case of a major outage or data loss. | infra-team
10 | Circuit breaker: | App

## Design-guideline
S.No. | SOLID Principle
1.1 | Single Responsibility Principle (SRP)
1.Does each class or module have a single responsibility or reason to change? 2.Are there any classes or methods that have multiple responsibilities? 3.Can the responsibilities of a class or module be clearly defined and described concisely?
1.2 | Open-Closed Principle (OCP)
1.Are the classes or modules open for extension but closed for modification? 2.Can new behaviour be added without modifying existing code? 3.Is inheritance or composition used to achieve extensibility?
1.3 | Liskov Substitution Principle (LSP)
1.Do subclasses or derived classes adhere to the contract defined by the base class or interface? 2.Can an instance of a subclass be used interchangeably with an instance of its superclass or base class? 3.Are there any violations of behaviour or assumptions when substituting one implementation with another?
1.4 | Interface Segregation Principle (ISP)
1.Are interfaces focused on specific client needs and avoid being overly general? 2.Do clients depend only on the interfaces they use rather than depending on unnecessary methods? 3.Are there any interfaces with too many methods that might indicate the need for splitting them?
1.5 | Dependency Inversion Principle (DIP)
1.Are higher-level modules or classes dependent on abstractions rather than concrete implementations? 2.Do dependencies flow towards abstractions, not towards concrete implementations?

## Best practices
1 | Codebase: Maintain a single codebase for your application, version-controlled using a tool like Git. | Done
2 | Dependencies: Use a dependency management system, such as Maven or Gradle, to handle external dependencies in your Spring Boot project.
3 | Configuration: Store configuration settings in the environment, preferably using environment variables or cloud-based configuration services like Spring Cloud Config.
4 | Backing Services: Treat any external services (databases, caches, messaging systems) as attached resources and access them via standardized protocols (e.g., JDBC for databases).
5 | Build, Release, Run: Keep the build, release, and run stages separate. Use build automation tools like Maven or Gradle to create a deployable artifact that can be released and run in different environments.
6 | Processes: Design your application as stateless processes that can be easily scaled horizontally. Utilize the containerization capabilities of tools like Docker to encapsulate your application.
7 | Port Binding: Let the web server provided by Spring Boot handle the port binding for your application. You don't need to explicitly handle it.
8 | Concurrency: Leverage Spring Boot's support for concurrency and asynchronous processing using features like the
@Async
annotation or Spring's
TaskExecutor
.
9 | Disposability: Design your Spring Boot application to be disposable, allowing it to start up quickly and shut down gracefully.
10 | Dev/Prod Parity: Keep your development, staging, and production environments as similar as possible to avoid unexpected issues. Use containerization and automation tools to achieve consistency.
11 | Logs: Write application logs to standard output (stdout) and avoid writing to local disk. Use logging frameworks supported by Spring Boot, such as Logback or Log4j2.
12 | Admin Processes: Create administrative tasks as separate processes that can be run independently, rather than bundling them with the main application.
13 | Stateless Processes: Design your Spring Boot application to be stateless, so it can easily scale horizontally and be resilient to failures.
14 | Portability: Build your application to be portable and deployable to various platforms and cloud providers. Use Spring Boot's cloud-native features and containerization tools like Docker and Kubernetes.
15 | Environment Parity: Aim to keep your development, staging, and production environments as close as possible to ensure consistency and avoid environment-specific issues. | Profile | Application | DevOps
|  |  | Application-dev.properites Application-uat.properites | Docker file ENTRYPOINT ["java", "-Dspring.profiles.active=UAT", "-jar", "/app.jar"]