## Sheet1
| Tech issues | Subtasks | Resource Name | Priority | Start Date | End Date | Remarks | Impact
1 | BAR Code Scanner : POC, and New Solution
|  | POC-Application should work in offline mode | Ponnusamy/Imaran | 1 | 2023-08-18 | 2023-08-25
|  | Impl- Application should work in offline mode | Ponnusamy/Imaran | 1
|  | POC-Browser based application read data from Barcode scanner USB drive | Gaurav | 1 | 2023-08-17 | 2023-08-25 | Timelines depends if we get sample barcode guns on 17th August, Admin rights to try some Drivers, Not able to connect Toyota systems like DB and SCM after globalprotect working
|  | Impl:Browser based application read data from Barcode scanner USB drive | Gaurav | 1
2 | NFR : Microservices Architecture/design
|  | Wave1: DB Migration Oracle to MySql | Amrinder | 2 | 2023-08-21 | 2023-09-08
|  | Wave2: MySql to Java for Microservices | xxxx | 2
3 | NFR : Authentication and Authorization
|  | Design & Architecture -Offline and online with SC2 | Gaurav | 4 | 2023-08-28 | 2023-09-12 | SC2 authentication complete Details, SC2 working sample credentials, Toyota Azure AD access or details for some users , Role Mappings for different use cases
|  | Impl-Offline and online with SC2 | Gaurav/Peeranut | 4
4 | NFR - Sprint Batch framework | Boiler plate code | Vijay | 3 | 2023-08-17 | 2023-08-25