## Cover
Phase | IMP | Project | TPEX Development Servers | [8 empty] | Page
Block |  | Infrastructure |  |  |  | Function | Infrastructure Design Document | Created | 2022-09-19 |  | by |  | FTH) Denny
Document |  | Installation Checklist for On-Premise |  |  |  | Title | Cover | Revised | 2022-09-28 |  | by |  | FTH) Denny
Installation Checklist for On-Premise
TPEX Development Servers
2022-09-28
Version. 0.1
Approved
Confidential

## Revision History
Phase |  | IMP |  |  | Project |  | TPEX Development Servers | [7 empty] | Page
Block |  |  |  |  | Infrastructure |  |  |  | Function | Infrastructure Design Document | Created | 2022-09-19 |  | by |  |  | FTH) Denny
Document |  |  |  |  | Installation Checklist for On-Premise |  |  |  | Title | Revision History | Revised | 2022-09-28 |  | by |  |  | FTH) Denny
[11 empty] | Class |  | A:add U:Update D:Delete
REVISION HISTORY
| Ver. |  | Num. | Date |  | Class | Sheet | Detail Modification | [7 empty] | by
| 0.0 |  | 1 | 2022-09-19 |  | A | All | Initial | [7 empty] | FTH) Denny
| 0.1 |  | 2 | 2022-09-28 |  | A | All | Update version 0.1 | [7 empty] | FTH) Denny

## Contents
Phase |  | IMP | Project | TPEX Development Servers | [5 empty] | Page
Block |  |  | Infrastructure |  | Function | Infrastructure Design Document | Created | 2022-09-19 | by |  | FTH) Denny
Document |  |  | Installation Checklist for On-Premise |  | Title | Table of Contents | Revised | 2022-09-28 | by |  | FTH) Denny
TABLE OF CONTENTS
|  | 0 | Overview
|  | 1 | System Outline
|  | 2 | Server Installation Checklist
|  | 2-1 | Server Installation Checklist for Container (OCP-DEV)
|  | 2-2 | Server Installation Checklist for Container (OCP-TRIAL)
|  | 2-3 | Server Installation Checklist for Container (OCP-UT)
|  | 2-4 | Server Installation Checklist for Linux Server : Database server
|  | 3 | Installation Checklist Sign-Off
|  | 4 | Hand Over Sign-Off

## Overview
Phase |  | IMP |  | Project |  | TPEX Development Servers | [13 empty] | Page
Block |  |  |  | Infrastructure |  |  |  |  | Function |  | Infrastructure Design Document |  |  | Created |  | 2022-09-19 |  |  | by |  | FTH) Denny
Document |  |  |  | Installation Checklist for On-Premise |  |  |  |  | Title |  | Desigh and Approach |  |  | Revised |  | 2022-09-28 |  |  | by |  | FTH) Denny
Overview
Infra. Implementation and Quality Check Process
Mile Stone & Process
|  | Solution & Budgetary Approval |  |  | Requirement Confirmation |  |  |  |  | Implemenation, Infra. Test, Quality Check and Hand-Over | [7 empty] | Before Golive Support |  |  | After Golive
| PIC | App-PIC |  | App-Mgr. | Project-PIC |  | Project-PIC | Infra.-PIC |  | Project-PIC |  | Project-PIC | Project-PIC |  | Infra.-PIC |  | Project-PIC | App-PIC |  |  | App-PIC
|  | Infra.-PIC |  | Infra.-Mgr | Infra.-PIC |  |  | Project-PIC |  |  |  |  | Infra.-PIC |  | Project-PIC |  | Infra.-PIC | Project-PIC (Opt.) |  |  | Onsite-Team
[5 empty] | App-PIC | [11 empty] | App-PIC | Infra. PIC (Opt.)
Onsite-Team
Development
Production
Work Sheet
CR
Deliverable
|  |  | - Project Approval |  |  | - System Outline |  |  |  |  | - Project Management (Daily Plan) | [6 empty] | - Perf. Report
|  |  | (TDEM Internal) |  |  | - Installation Checklist |  |  |  |  | - Poject Delivery Document (Details Design Doc, Infra. Test Evident, One Page) | [6 empty] | (Optional)
[6 empty] | - Requirement Sign-Off |  |  |  |  | - Hand Over Sign-Off
- LOA Signed by Infra. Manager
- CSAT Signed by Infra.-PIC
❶ System Outline
❷ Installation Checklist
❸ Requirement Sign-Off
Requirement
Sign-Off
❹ Production Hand Over Sign-Off
Hand
Over
Proejct Approval by
App & ITO Manager
Quality Gate
before start
Implement
Quality Gate
before
Hand-Over
Project Finish
(Closure)
Infra. Tasks Completed
Get LOA & CSAT
Project Start
(Kick-Off)
❹ Developmen Hand Over Sign-Off
Development
Hand Over
Sign-Off
Golive
Major change : To GM(App, Infra) + Reason to change
** Other change -> App team request by Email , Infra Update Issue list, Installation Checklist
** Ensure all request will update to Installation checklist & Design
Quality
Check
Installation Checklist
Final System Requirement Confirmation
Project
Approved
Final Solution &
Budgetary
Infra. Test
Development
Implementation
After
Golive Support
Perf. Test
(Optional)
Destials
Design
Hand
Over
Production
Hand Over
Sign-Off
Quality
Check
Infra. Test
Production
Implementation
Destials
Design

## 1
1. System Outline Diagram
>
Security Center
ป
Database Server
THDS9DBD01
Oracle DB 19C Enterprise
Public IP: X.X.X.X
Developer
(TDEM)
Oracle Linux 8.6
CPU 4 vCPU
MEM 16 GB
100 GB
(OS)
2360 GB
(DB)
2780 GB
(FS)
Deep Security
& Tanium
Zabbix
System Monitoring
No Backup
TPEX Development Servers
Moderna (TADC)
Jump Server
10.251.243.11
10.251.243.12
SMTP
DB Schema #1
DB Schema #2
DB Schema #3
User
(TDEM/TMT/STM)
Instance : DS9DEVT
TDEM VPN
BFW Schema
Instance : BFWDEVT
Application Area
Storage
BFW 3.0
/home/TMAP/ST/shared
Storage
HULFT 8.0
/GFTS
Storage
IBM Workload Scheduler 9.5
/opt/TWS
Storage
Vuteq (Supplier)
Oracle KVM
At begining planned to utilize FullGW as file transfer system, And planned to migrate to HULFT step by step (TBC with App team)
Global File Transer
WFH
RDP:
3389
'/home/TMAP/DSD/shared
'/home/TMAP/DST/shared
'/home/TMAP/DSU/shared
Full Gateway
/ZD
Storage
Full Gateway Transfer
Internal Network
Firewall
Supplier Network
HTTPS
(443)
UT
DEV
TRIAL
DS9USER00
DS9USER01
DS9USER02
BFWUSER00
https://sc2-dev.tmap-em.toyota-asia.com
Phase
Project
TPEX Development Servers
IMP
Page
Block
Infrastructure
System Structure Design Document
Created
1 Sep, 2022
Function
FTH) Supakorn
by
Document
System Architecture
System Outline Diagram
Revised
24 Oct, 2022
Title
FTH) Supakorn
by
OCP Cluster Development
Worker Node x4
DS9DEV
Egress IP : X.X.X.X
Service x 30
POD x 1
Spec : 5 vCPU / 20 GB
Authentication Service
Authentication
SMTP
Load balancer
URL : tpex-dev.tdem.toyota-asia.com
URL : tpex-trial.tdem.toyota-asia.com
URL : tpex-ut.tdem.toyota-asia.com
IP : 10.249.1.XXX
Port : TCP 443
DS9TRIAL
Egress IP : X.X.X.X
Spec : 6 vCPU / 20 GB
Authentication Service
Authentication
SMTP
DS9UT
Egress IP : X.X.X.X
Spec : 6 vCPU / 20 GB
Authentication Service
Authentication
SMTP
Geotrust OV
Service x 30
POD x 1
Geotrust OV
Service x 30
POD x 1
Geotrust OV
SSH, SFTP:
22
DS9 DB
(8521)
BFW DB
(8520)
Create Service/POD by App team
Create Service/POD by App team
Create Service/POD by App team
WAF
Firewall
TDEM
Local Gateway
TDEM
Full Gateway
check folder structure with onsite team

## TBC
Phase |  | IMP | Project | TPEX Development Servers | [5 empty] | Page
Block |  |  | Infrastructure |  | Function | Infrastructure Design Document | Created | 2022-09-19 | by |  | FTH) Denny
Document |  |  | Installation Checklist for On-Premise |  | Title | Desigh and Approach | Revised | 2022-09-28 | by |  | FTH) Denny
1. System Outline
CI / CD
Firewall
Firewall
TDEM User
Developer
Development Environment
Firewall
Database Server
THXXXDBD01
ROEM DB Service:
Port: 8521
Oracle 19c ENT
Public IP: 10.251.107.XXX
DB Name
XXXUSER01
XXXUSER00
XXXUSER02
NFS Share
Application NFS Share
DEV
uusdavd: /home/TMAP/DAV/shared
BCT
uusdast: /home/TMAP/DAS/shared
UAT
uusdaut: /home/TMAP/DAU/shared
DB Name
BFW Deamon
BFW DB Service:
Port: 8520
BFWUSER00
IBM Workload Scheduler 9.5
SMTP
Oracle Linux 8.6 64 bit
CPU 4 vCPU
MEM 16 GB
100 GB
(OS)
2,360 GB
(DB Disk)
Deep Security
& Tanium
Zabbix
System Monitoring
OCP Cluster Development
Worker Node x4
Firewall
Production Environment
Load balancer
URL : roem.tdem.toyota-asia.com
IP : 10.249.1.11
Port : TCP 443
OPC Cluster Production
Worker Node x4
PROD
Egress IP : 10.249.206.XXX
Service1
POD
POD
POD
Service2
POD
POD
POD
Spec : 28 vCPU / 101 GB
Authentication Service
Authentication
Application Deploy
Jump Server
Database Server
THXXXDBP01
Public IP: 10.251.7.XX
SMTP
Oracle Linux 8.6 64 bit
CPU 6 vCPU
MEM 26 GB
100 GB
(OS)
Deep Security
& Tanium
Zabbix
System Monitoring
CommVault
Backup
sc2.tmap-em.toyota-asia.com
HTTPS
Access Application after Logged in
Remote Destop
User can be request direct connect for DB management Tool by Firewall port : 8520 & 8521
sc2.dev.tmap-em.toyota-asia.com
HTTPS
WFH
TDEM VPN
SMTP
Login
Kong API GW PROD
DA9BCT
Egress IP : 10.249.216.XXX
Service1
POD
Service2
POD
Spec : 6 vCPU / 20 GB
Authentication Service
Authentication
SMTP
POD
POD
DA9UAT
Egress IP : 10.249.216.XXX
Service1
POD
Service2
POD
Spec : 6 vCPU / 20 GB
Authentication Service
Authentication
SMTP
POD
POD
Support by EPA
Support by EPA
Kong API GW DEV
SSH
DA9DEV
Egress IP : 10.249.216.XXX
Service1
POD
Service2
POD
Spec : 5 vCPU / 20 GB
Authentication Service
Authentication
SMTP
POD
POD
Support by EPA
Load balancer
URL : roem-dev.tdem.toyota-asia.com
URL : roem-bct.tdem.toyota-asia.com
URL : roem-uat.tdem.toyota-asia.com
IP : 10.249.1.21
Port : TCP 443
3,290 GB
(DB Disk)
3,120 GB
(FS Disk)
Shared Disk
Database Server
THXXXDBP02
Public IP: 10.251.7.XX
SMTP
Oracle Linux 8.6 64 bit
CPU 6 vCPU
MEM 26 GB
100 GB
(OS)
Deep Security
& Tanium
Zabbix
System Monitoring
CommVault
Backup
ROEM Service:
Port: 8521
DB Name
DB Users
XXXUSER01
XXXUSER00
XXXUSER02
DB Name
DB Users
BFW Deamon
NFS Share
PRD
XXXuser00: /home/TMAP/XXX/shared
Application NFS Share
BFW Service:
Port: 8520
BFWUSER00
IBM Workload Scheduler 9.5
3,180 GB
1100GB
3,120 GB
XXXPROD
BFWPROD
PRD
uusst00: /home/TMAP/ST/shared
Oracle 19c ENT
Cluster Service
2,780 GB
(FS Disk)
PROD Environment
TBC

## 2-1 (OCP-DEV)
2. Server Installation Checklist
2-2. OCP Cluster Development
|  |  |  | Before Start Implementation | Before Hand Over
Item |  | Setup Value |  | Requirement Confirmation | Quality Check Result | Remark
Environment |  | DEV
Project Namespace | PROJECT_NAME: | ds9-dev
| SERVICE_ACCOUNT: | git-svc-acc-ds9-dev
| AD_GROUP_NAME: | CIP-TDEM-OCP-FTH-DS9 |  |  |  | Need App team to request create group and user with CPS team
| PROJECT_ADMIN_USER: | thitipong_kan |  |  |  | Need to confirm with App team
| PROJECT_DESCRIPTION: | TPEX DEV
Web URL | URL: | -
Name Space / Env. | CPU Cores : | 5 vCPU
| Memory : | 20 GB
Network Specification | Application URL: | tpex-dev.tdem.toyota-asia.com |  |  |  | App team need to create service first
| Ingress IP: | 10.249.1.XXX
| Egress IP: | 10.249.216.XXX |  |  |  | add certificate apply
Image Selection |  | Image Name | Image Version
|  | Node.js (16.13.1) |  |  |  | Need to confirm with App team
|  | Java Spring Boot (2.6.1) |  |  |  | Need to confirm with App team
|  | React (17.2) |  |  |  | Need to confirm with App team
ITO will check with COE for all options
[7 empty] | Requirement Confirmation | Quality Check Result
[7 empty] | Confirmed | Pass
[7 empty] | N/A | Not Pass
Phase
Project
TPEX Development
IMP
Page
Block
Infrastructure
System Structure Design Document
Created
19-Sep-2022
Function
FTH) Denny
by
Document
Installation Checklist
Server Installation Checklist
Revised
28-Sep-2022
Title
FTH) Denny
by
2-2
Note on E11: Manut, Khanadnid: User-Token yJhbGciOiJSUzI1NiIsImtpZCI6IlU0TldWc3d0ZDc0ZGxNQzdpOERqMmxndHQ2MXhvZFZLQmhYSldrc05lSGsifQ.eyJpc3MiOiJrdWJlcm5ldGVzL3NlcnZpY2VhY2NvdW50Iiwia3ViZXJuZXRlcy5pby9zZXJ2aWNlYWNjb3VudC9uYW1lc3BhY2UiOiJjZjktZGV2Iiwia3ViZXJuZXRlcy5pby9zZXJ2aWNlYWNjb3VudC9zZWNyZXQubmFtZSI6ImdpdC1zdmMtYWNjLWNmOS1kZXYtdG9rZW4tYjhnOXEiLCJrdWJlcm5ldGVzLmlvL3NlcnZpY2VhY2NvdW50L3NlcnZpY2UtYWNjb3VudC5uYW1lIjoiZ2l0LXN2Yy1hY2MtY2Y5LWRldiIsImt1YmVybmV0ZXMuaW8vc2VydmljZWFjY291bnQvc2VydmljZS1hY2NvdW50LnVpZCI6IjlkNjg2ODhjLTZiYmYtNGVkOS1hZmJmLTc0ZGJjMTRhNjY1MyIsInN1YiI6InN5c3RlbTpzZXJ2aWNlYWNjb3VudDpjZjktZGV2OmdpdC1zdmMtYWNjLWNmOS1kZXYifQ.CBjH9GWQ1s3fOHQAjv94e_8A21sHvCjvca-mYJcftJA-N6t-1AJEE_4ETnX3CAbpgvrVh_X8jsMwdFu0cVNSdSB_fKKh1yZWJzxJf95KGVsecO3KX8XcESH7hQ0B1w-8MRJA3TFiZ_us_OBTtwC49EvakxvB2-jHUpr6CXuN8hfXyXWzVFA-eRa-2jMU6vUKnD9SMJzSI4T7OUnxaIuWGVvhAtF09gVTyk3RyY8cBlIP-aGkhleL7t30PbO05qdqHJ-EykolzsBk0q4zrFOeGp_qd2xJUiC0g3quYH5cAPWQJOE9Ug_YSajnh1UbgI1OlOJ14O5xoMIN9o6ReB_9zg

## 2-2 (OCP-TRIAL)
2. Server Installation Checklist
2-2. OCP Cluster Development
|  |  |  | Before Start Implementation | Before Hand Over
Item |  | Setup Value |  | Requirement Confirmation | Quality Check Result | Remark
Environment |  | TRIAL
Project Namespace | PROJECT_NAME: | ds9-trial
| SERVICE_ACCOUNT: | git-svc-acc-ds9-trial
| AD_GROUP_NAME: | CIP-TDEM-OCP-FTH-DS9 |  |  |  | Need App team to request create group and user with CPS team
| PROJECT_ADMIN_USER: | thitipong_kan |  |  |  | Need to confirm with App team
| PROJECT_DESCRIPTION: | TPEX TRIAL
Web URL | URL: | -
Name Space / Env. | CPU Cores : | 6 vCPU
| Memory : | 20 GB
Network Specification | Application URL: | tpex-trial.tdem.toyota-asia.com
| Ingress IP: | 10.249.1.XXX
| Egress IP: | 10.249.216.XXX
Image Selection |  | Image Name | Image Version
|  | Node.js (16.13.1) |  |  |  | Need to confirm with App team
|  | Java Spring Boot (2.6.1) |  |  |  | Need to confirm with App team
|  | React (17.2) |  |  |  | Need to confirm with App team
[7 empty] | Requirement Confirmation | Quality Check Result
[7 empty] | Confirmed | Pass
[7 empty] | N/A | Not Pass
Phase
Project
TPEX Development
IMP
Page
Block
Infrastructure
System Structure Design Document
Created
19-Sep-2022
Function
FTH) Denny
by
Document
Installation Checklist
Server Installation Checklist
Revised
28-Sep-2022
Title
FTH) Denny
by
2-2
Note on E11: Manut, Khanadnid: User_Token eyJhbGciOiJSUzI1NiIsImtpZCI6IlU0TldWc3d0ZDc0ZGxNQzdpOERqMmxndHQ2MXhvZFZLQmhYSldrc05lSGsifQ.eyJpc3MiOiJrdWJlcm5ldGVzL3NlcnZpY2VhY2NvdW50Iiwia3ViZXJuZXRlcy5pby9zZXJ2aWNlYWNjb3VudC9uYW1lc3BhY2UiOiJjZjktdWF0Iiwia3ViZXJuZXRlcy5pby9zZXJ2aWNlYWNjb3VudC9zZWNyZXQubmFtZSI6ImdpdC1zdmMtYWNjLWNmOS11YXQtdG9rZW4tcnJkbXgiLCJrdWJlcm5ldGVzLmlvL3NlcnZpY2VhY2NvdW50L3NlcnZpY2UtYWNjb3VudC5uYW1lIjoiZ2l0LXN2Yy1hY2MtY2Y5LXVhdCIsImt1YmVybmV0ZXMuaW8vc2VydmljZWFjY291bnQvc2VydmljZS1hY2NvdW50LnVpZCI6ImJkMjUzNjc1LTViOGEtNGFiZS1hZGViLWQxNzQ2NmJmNzdkZSIsInN1YiI6InN5c3RlbTpzZXJ2aWNlYWNjb3VudDpjZjktdWF0OmdpdC1zdmMtYWNjLWNmOS11YXQifQ.KVgAVdPiIhJDmSzEM9-gTtkGURghqDwEru3tQldKPYEO954pRA175MiVLnnzm0-sYGDhtPtwXcWIc6gviAg1SwVBjuICi27l33Kditkvg0F5ixkilt68Tad5ycmPPqQyHjokNz2OHARhoyHkpAzVFJ1VfxOXjOMmIiNXkfkpgUO_RNiZ0xjd6JgJKQ9t4s8o4JchdqJA0wf7reeVbKLZ6kVra55lDlqsEak5x9BWx88KnFKIqoY9GHs02GVf0g-07CXA9WxcutPdT0DpT-TYM8lMDuJWUiQS2HUlNEzmrSNnLn7jh0BdPwo6QM0cwVRYdpRwnsAmZkDXXq_s90NJMg

## 2-3 (OCP-UT)
2. Server Installation Checklist
2-2. OCP Cluster Development
|  |  |  | Before Start Implementation | Before Hand Over
Item |  | Setup Value |  | Requirement Confirmation | Quality Check Result | Remark
Environment |  | UT
Project Namespace | PROJECT_NAME: | ds9-ut
| SERVICE_ACCOUNT: | git-svc-acc-ds9-ut
| AD_GROUP_NAME: | CIP-TDEM-OCP-FTH-DS9 |  |  |  | Need App team to request create group and user with CPS team
| PROJECT_ADMIN_USER: | thitipong_kan |  |  |  | Need to confirm with App team
| PROJECT_DESCRIPTION: | TPEX UT
Web URL | URL: | -
Name Space / Env. | CPU Cores : | 6 vCPU
| Memory : | 20 GB
Network Specification | Application URL: | tpex-ut.tdem.toyota-asia.com
| Ingress IP: | 10.249.1.XXX
| Egress IP: | 10.249.216.XXX
Image Selection |  | Image Name | Image Version
|  | Node.js (16.13.1) |  |  |  | Need to confirm with App team
|  | Java Spring Boot (2.6.1) |  |  |  | Need to confirm with App team
|  | React (17.2) |  |  |  | Need to confirm with App team
[7 empty] | Requirement Confirmation | Quality Check Result
[7 empty] | Confirmed | Pass
[7 empty] | N/A | Not Pass
Phase
Project
TPEX Development
IMP
Page
Block
Infrastructure
System Structure Design Document
Created
19-Sep-2022
Function
FTH) Denny
by
Document
Installation Checklist
Server Installation Checklist
Revised
28-Sep-2022
Title
FTH) Denny
by
2-2
Note on E11: Manut, Khanadnid: User_Token eyJhbGciOiJSUzI1NiIsImtpZCI6IlU0TldWc3d0ZDc0ZGxNQzdpOERqMmxndHQ2MXhvZFZLQmhYSldrc05lSGsifQ.eyJpc3MiOiJrdWJlcm5ldGVzL3NlcnZpY2VhY2NvdW50Iiwia3ViZXJuZXRlcy5pby9zZXJ2aWNlYWNjb3VudC9uYW1lc3BhY2UiOiJjZjktdHJpYWwiLCJrdWJlcm5ldGVzLmlvL3NlcnZpY2VhY2NvdW50L3NlY3JldC5uYW1lIjoiZ2l0LXN2Yy1hY2MtY2Y5LXRyaWFsLXRva2VuLXd3aDJsIiwia3ViZXJuZXRlcy5pby9zZXJ2aWNlYWNjb3VudC9zZXJ2aWNlLWFjY291bnQubmFtZSI6ImdpdC1zdmMtYWNjLWNmOS10cmlhbCIsImt1YmVybmV0ZXMuaW8vc2VydmljZWFjY291bnQvc2VydmljZS1hY2NvdW50LnVpZCI6IjM2NDQ3MDc2LTAxZjQtNDg2OC1hMzJmLWYxMjM1NjViNzRlMyIsInN1YiI6InN5c3RlbTpzZXJ2aWNlYWNjb3VudDpjZjktdHJpYWw6Z2l0LXN2Yy1hY2MtY2Y5LXRyaWFsIn0.OEaniSjsksEcnbIFFO7EdrVsmv3Z-d1XZi_Dr9VCzltu-LPJ4MGU68L9RIG04ezqBn6MPFno9doVsgjk9M5kSF4w3MjLd7p7u29AdXKAvJXZnr_upO0C8xtI611PNMbQSHWGucfZS_6wA5ffKTBnH-Eiv60kgdWIULKbwYNfhhX2r_gpgITRsstplRkUwEZorH8PBHC8u353ozd75-L6IDBWUgCgE8RSBlL9twUh9M2Q1xfbF9vjMtUwpD4yF3-w40ugnBqGK2JorttC-TPJGYKok6Dbre3PIo4dwCPJcGw7LT9Tjdkq-JHz7jBh7m-TkE_ACsGbezvL7L6gGQ6jNQ

## 2-4 (DB)
2. Server Installation Checklist
2-1) Development Database Server | [5 empty] | Before Start Implementation | Before Hand Over
Item |  | Setup Value |  |  |  | Requirement Confirmation | Quality Check Result | Remark
Environment |  | Development
Server Description |  | Database Server
Catalog Name |  | Oracle Linux 8.6, 64Bits + Oracle DB 19C Enterprise (Oracle KVM)
Hostname |  | THDS9DBD01
Domain |  | tdem.toyota-asia.com
Operating System |  | Oracle Linux 8.6, 64 bits
Server Specification | CPU Cores : | 4 vCPU
| Memory : | 16 GB
| Assigned Disks to VM : | Disk1 (OS): | 100 GB
|  | Disk2 (DB): | 2,360 GB
|  | Disk3 (File System): | 2,780 GB
Network Specification | DNS Registered Name : | -
| DNS Registered IPs : | -
| Virtual IP : | -
| Virtual Hostname : | -
| Network Segment : | Development Database Segment
| IP Address (Public) : | Ethernet 0 | IP: 10.251.107.XXX | GW: 10.251.107.254 | VLAN : 407
IP Address (etc.) :
| Netmasks : | 255.255.255.0
| Default Gateway : | 10.251.107.254
| DNS Primary : | 10.254.1.133
| DNS Secondary : | 172.17.1.133
| NTP Server : | ntp.tdem.toyota-asia.com
| SMTP (Mail) Server : | smtp.ap.toyota-asia.com
|  | Request register Mail relayed | [5 empty] | (TBC for external mail)
Disk Layout | System Disk (OS) : | Partition | Size (GB)
|  | / | 10
|  | /usr | 10
|  | /var | 20
|  | /opt | 35
|  | /tmp | 10
|  | swap | 8
|  | /home | 5
|  | /boot | 1
|  | /boot/efi | 1
| DB Disk (Disk2) : | File System | Size | Disk Group
| ROEM DEV Database : | /opt/oracle/DS9/datafile/Table | 1280 | DB_VG01 (ROEM & BFW Database)
|  | /opt/oracle/DS9/datafile/Temp | 50
|  | /opt/oracle/DS9/datafile/System | 20
|  | /opt/oracle/DS9/datafile/Undo1 | 50
|  | /opt/oracle/DS9/redo11 | 8
|  | /opt/oracle/DS9/redo12 | 8
|  | /opt/oracle/DS9/ctl1 | 4
|  | /opt/oracle/DS9/ctl2 | 4
|  | /opt/oracle/DS9/ora_exp | 640
| BFW Databae : | /opt/oracle/ST/datafile/Table | 20
|  | /opt/oracle/ST/datafile/Temp | 20
|  | /opt/oracle/ST/datafile/System | 10
|  | /opt/oracle/ST/datafile/Undo1 | 20 | [5 empty] | 2360
|  | /opt/oracle/ST/redo11 | 8 | [5 empty] | 2168
|  | /opt/oracle/ST/redo12 | 8 | [5 empty] | 192
|  | /opt/oracle/ST/ctl1 | 4
|  | /opt/oracle/ST/ctl2 | 4
|  | /opt/oracle/ST/ora_exp | 10 | [5 empty] | 118
| File System Disk (Disk3): | /opt/TWS | 30 | FS_VG02 (ROEM Filesystem Data)
|  | /GFTS | 20
|  | /ZD | 20 |  |  |  |  | confirm file structure with PLS | 896.6667
|  | /home/TMAP/ST | 20
|  | /home/TMAP/DSD | 850 |  |  |  |  | For DEV | 2780
|  | /home/TMAP/DST | 850 |  |  |  |  | For TRIAL | 2640
|  | /home/TMAP/DSU | 850 |  |  |  |  | For UT | 140
OS User |  | User | Group | Home Directory | Permission
|  | root | root | /root | Admin previledge
|  | oracle | oinstall dba | /home/oracle | Owner full access
|  | maestro | tivoli | /opt/TWS/maestro | Owner full access
|  | uusst00 | ugradm0 | /home/TMAP/ST | Owner full access
|  | ds9user00 | ugrdl00 | /home/TMAP/DSD | Owner full access |  |  | fo DEV
|  | ds9user01 | ugrdl00 | /home/TMAP/DST | Owner full access |  |  | for TRIAL
|  | ds9user02 | ugrdl00 | /home/TMAP/DSU | Owner full access |  |  | for UT
Additional Package |  | Package Name
|  | Oracle Database | Oracle Database 19C Enterprise | Mandatory
|  | Job Scheduler | IBM Tivoli Workload Scheduler 9.5 | Mandatory
|  | HULFT | Hulft 8.0 | Mandatory
|  | Full Gateway | Full Gateway | Mandatory
|  | BFW | BFW 3.0 | Mandatory
|  | Zabbix | Zabbix 4.4.8 | Mandatory
|  | Deep Security | Deep Security 20.0.0 | Mandatory
|  | Tanium | Tanium 7.4.4 | Mandatory
Port Summary |  | Service | Access Port
|  | SSH,SFTP | 22
|  | Mail | 25
|  | NFS | 111, 2049
|  | Database Instance | 8520, 8521
NFS Summary | NFS Server | Destination Server | Source Directory | Mount Point | Permission
|  | <DB Server IP> <Update after provisioned> | /home/TMAP/DSD/shared | /home/TMAP/DSD/shared | Owner full access |  |  | DEV
|  | <DB Server IP> <Update after provisioned> | /home/TMAP/DST/shared | /home/TMAP/DST/shared | Owner full access |  |  | TRIAL
|  | <DB Server IP> <Update after provisioned> | /home/TMAP/DSU/shared | /home/TMAP/DSU/shared | Owner full access |  |  | UT
|  | <DB Server IP> <Update after provisioned> | /home/TMAP/ST/shared | /home/TMAP/ST/shared | Owner full access |  |  | BFW (confirm with App)
| NFS Client | Destination Server | Destination Mount Directory | Mount Point | Permission
N/A
Database Configuration |  | Instance/Parameter | Setup Value
|  | Installation path | /opt/oracle/product/19.3.0/db_1
TPEX Instance
|  | Instance Name | DS9DEVT | Follow existing value
|  | Database Name | DS9DEVT | Follow existing value
|  | TNS name | DS9DEVT | Follow existing value
|  | Listener name | LISTENER_DS9DEVT00 | Follow existing value
|  | Database Files Location | /opt/oracle/DS9 | Follow existing value
|  | DB Port no | 8521 | Follow existing value
|  | NLS_LANGUAGE/NIS_TERRITORY | AMERICAN/AMERICA | Follow existing value
|  | NLS_CHARACTERSET | TH8TISASCII | Follow existing value
|  | NLS_NCHAR_CHARACTERSET | AL16UTF16 | Follow existing value
|  | SGA Size | 2,163 MB | Existing Sizing + Growth 5%/Yr, 3 Yrs | Existing = 2,163 MB
|  | PGA Size | 1,165 MB | Existing Sizing + Growth 5%/Yr, 3 Yrs | Existing = 1,165 MB
|  | User Table Space | TBSP_USER00 | System Standard
|  | Index Table Space | TBSP_INDEX00 | System Standard
|  | db_files | 1000 | Follow existing value | Existing = 1000
|  | db_block_size | 8192 | Follow existing value | Existing = 8192
|  | Processes | 600 | Follow existing value | Existing = 600
|  | job_queue_processes | 60 | Follow existing value | Existing = 600
|  | open_cursors | 600 | Follow existing value | Existing = 600
|  | parallel_max_servers | 2 | Follow existing value | Existing = 2
|  | DB Size | 600,000 MB | Follow system requirement | Existing = 90 GB; requirement : 320 GB for TMT
|  | Index Size | 150,000 MB | Follow system requirement (25% of Data) | Existing = 15 GB (17% of Data)
|  | Undo | 40,000 MB | Recommend value | Existing = 16 GB
|  | Temp | 40,000 MB | Recommend value | Existing = 4 GB
|  | System | 10,000 MB | Recommend value | Existing = 910 MB
|  | Infra | 2,048 MB | Recommend value | Existing = 2 GB
|  | SYSAUX | 3,072 MB | Recommend value | Existing = 3 GB
|  | Redo 1 | 6,144 MB | Recommend value | Existing = 5 * 500 MB
|  | Control 1 | 3,072 MB | Recommend value | Auto generate during DB creation
|  | Redo 2 | 6,144 MB | Recommend value | Existing = 5 * 500 MB
|  | Control 2 | 3,072 MB | Recommend value | Auto generate during DB creation
|  | Archive | 0 MB | No Archive for DEV environment
|  | Export Area | 350,000 MB | 50% of Data + index
|  | Schema 1: DS9ADM | Group : DS9 Admin | Password : DS9ADM00
|  | Schema 2: DS9USERVD | Group : Development | Password : DS9USERVD |  |  |  | DEV
|  | Schema 3: DS9USERST | Group : TRIAL | Password : DS9USERST |  |  |  | TRIAL
|  | Schema 4: DS9USERUT | Group : UT | Password : DS9USERUT |  |  |  | UT
BFW Instance
|  | Instance Name | BFWDEVT | Follow existing value
|  | Database Name | BFWDEVT | Follow existing value
|  | TNS name | BFWDEVT | Follow existing value
|  | Listener name | LISTENER_BFWDEVT00 | Follow existing value
|  | Database Files Location | /opt/oracle/ST
|  | DB Port no | 8520
|  | NLS_LANGUAGE/NIS_TERRITORY | AMERICAN/AMERICA | Follow existing value
|  | NLS_CHARACTERSET | TH8TISASCII | Follow existing value
|  | NLS_NCHAR_CHARACTERSET | AL16UTF16 | Follow existing value
|  | SGA Size | 1400MB | Recommend value
|  | PGA Size | 300MB | Recommend value
|  | User Table Space | TBSP_USER00
|  | Index Table Space | TBSP_INDEX00
|  | db_files | 1000 | Follow existing value
|  | db_block_size | 8192 | Follow existing value
|  | Processes | 100 | Recommend value
|  | job_queue_processes | 100 | Recommend value
|  | open_cursors | 100 | Recommend value
|  | parallel_max_servers | 5 | Follow existing value
|  | DB Size | 8,000 MB | Follow system requirement
|  | Index Size | 2,048 MB | Follow system requirement
|  | Undo | 2,000 MB | Recommend value
|  | Temp | 2,000 MB | Recommend value
|  | System | 2,048 MB | Recommend value
|  | SYSAUX | 1,024 MB | Recommend value
|  | Redo 1 | 6,144 MB | Recommend value
|  | Control 1 | 3,072 MB | Recommend value
|  | Redo 2 | 6,144 MB | Recommend value
|  | Control 2 | 3,072 MB | Recommend value
|  | Export Area | 0 MB | No Export for DEV environment
|  | Schema 1: BFWADM | Group : BFW Admin | Password : BFWADM
|  | Schema 2: BFWUSER00 | Group : BFW User | Password : BFWUSER00MA00
IBM Workload Scheduler |  | Configuration
|  | Installation path | /opt/TWS
|  | Installed module | MDM ( IBM Workload Scheduler master domain manager)
|  | Installed module | WAS (WebSphere Application Server Liberty base)
|  | Database Net service name | BFW
|  | System users | maestro
|  | BFW users | uusst00
HULFT Configuration |  | Configuration
|  | Installation path | /usr/local/HULFT/bin
|  | HULFPATH: | /usr/local/HULFT/etc
|  | Application Folder | /GFTS
Full Gateway |  | Configuration
|  | Installation path | /ZD
|  | Receive Folder | /ZD/RECV
|  | Send Folder | /ZD/SEND
Batch Framework Configuration |  | Configuration
|  | Installation path | /home/TMAP/ST
Monitoring Setting (Zabbix) |  | Configuration
|  | Join VM to Monitoring | Linux DEV Template
|  | Collect System performance | Enabled
|  | Enable Trigger Mail Alert | Disabled
Antivirus Setting (Deep Security) |  | Configuration
|  | Activate Policy | DB Server Policy
EDR Seting (Tanium) |  | Configuration
|  | Installed with standard config | Yes
VASCAN |  | Configuration
|  | VASCAN and Fix OS & installed Middleware | Yes
[9 empty] | Requirement Confirmation | Quality Check Result
[9 empty] | Confirmed | Pass
[9 empty] | N/A | Not Pass
Phase
Project
TPEX Development Server
IMP
Page
Block
Infrastructure
System Structure Design Document
Created
19 Sep, 2022
Function
FTH) Denny
by
Document
Installation Checklist
Server Installation Checklist
Revised
28 Sep, 2022
Title
FTH) Denny
by
add owner
add owner
check existing with K.Kiattiyot
compare with ROEM main

## 3_Requirement Sign-Off
Phase |  |  |  | Project | TPEX Development Servers | [7 empty] | Page
Block |  |  |  | Infrastructure |  | Function | Infrastructure Design Document |  |  | Created | 2022-09-19 | by |  | FTH) Denny
Document |  |  |  | Installation Checklist for On-Premise |  | Title | Desigh and Approach |  |  | Revised | 2022-09-28 | by |  | FTH) Denny
3. Installation Checklist Sign-Off
| System Name |  |  | TPEX |  |  | Project Code |  | DS9 |  | Department
Project Details
DESCRIPTION OF SERVICES TO BE PROVIDED
Project Name / Environment TPEX Development
|  |  | Service Delivery |  |  |  |  | Archived | Need Future Development | Ramark
Project Kick-Off with all parties (App-PIC, Infra.-PIC) to clearify the solution that already provided in UR Phase
Confirmed Server Sizing and Software Version
Provide *System Outline Diagram (Refer to Tab no. 1)
Provide and *Installation Checklist (Refer to Tab no. 2-x)
Requirement Confirmation with Infra.-PIC
Infra.-PIC approved to start implementation
The services have been performed in accordance with the Service Description described above
Installation Checklist Sign-Off:
Date:
Fujitsu
PIC
Application Team
PIC
Infrastructure Team
Manager
Date:
Date:
Name:
Manager
Date:
PIC
Manager
Name: Panuthat
Name: Narain
Name: Prachya
Date: 27.Sep.2022
Name: Denny
Date: 27.Sep.2022
Name: Denny

## 4_Hand Over Sign-Off
Phase |  |  |  | Project | TPEX Development Servers | [7 empty] | Page
Block |  |  |  | Infrastructure |  | Function | Infrastructure Design Document |  |  | Created | 2022-09-19 | by |  | FTH) Denny
Document |  |  |  | Installation Checklist for On-Premise |  | Title | Desigh and Approach |  |  | Revised | 2022-09-28 | by |  | FTH) Denny
4. Hand Over Sign-Off
| System Name: |  |  | ROEM Development |  |  | Project Code: |  | DS9 |  | Department:
Project Details:
DESCRIPTION OF SERVICES TO BE PROVIDED
Project Name / Environment TPEX Development
|  |  | Service Delivery |  |  |  |  | Archived | Need Future Development | Ramark
Server and Infrastructure Implemeantion completed
Infra. Test completed (including Evident Report)
No remaining technical issue
Quality Check Confirmed by Infra.-PIC
Submit Infrastructure Details Design Documents to Infra.-PIC
Performance Test Support before Golive (Optional)
Hand Over Server and Infrastructure to App-PIC
Hand Over Server and Infrastructure to Onsite Team
The services have been performed in accordance with the Service Description described above
Hand Over Sign-Off:
Date:
Fujitsu
PIC
Application Team
PIC
Infrastructure Team
Manager
Date:
Date:
Name:
Manager
Date:
PIC
Manager
Name: Panuthat
Name: Narain
Name: Prachya
Date: 27.Sep.2022
Name: Denny
Date: 27.Seo.2022
Name: Denny

## LSP&MMS (hidden)
LSP & MMS Sizing
New LSP Production Server Sizing
Server | CPU (Core) | Mem (GB) | OS Disk (GB) | Data Disk (GB)
DB | #REF! | #REF! | #REF! | #REF!
Web/App | #REF! | #REF! | #REF! | 0
Existing MMS Server Sizing
Server | CPU (Core) | Mem (GB) | OS Disk (GB) | Data Disk (GB)
DB | 2 | 20 | 150 | 300
Web/App | 1 | 16 | 120 | 0
LSP & MMS Final Sizing (Based on HP Private Cloud)
Server | RequireCPU (Core) | CPU Sizing (Core) | Require Mem (GB) | Mem Sizing (GB) | OS Disk (GB) | Required Disk(GB) | Data Disk Sizing (GB)
DB | #REF! | 5 | #REF! | 36 | 150 | #REF! | 3500
Web/App | #REF! | 4 | #REF! | 32 | 120 | 0 | 0
Additional Resource
Server | RequireCPU (Core) | CPU Sizing (Core) | Require Mem (GB) | Mem Sizing (GB) | OS Disk (GB) | Required Disk(GB) | Data Disk Sizing (GB)
DB |  | 3 |  | 16 | 0 |  | 3200
Web/App |  | 3 |  | 16 | 0 |  | 0
WebApp Server
Follow HP Cloud
Selecable Value
Note on I14: LSP-DB + MMS-DB (Utilize existing BFW)