## Sheet1
Mar-2023
Sno. | Activity |  | PIC | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | Status
1 | Server Readiness | [17 empty] | 2 Issues reported by team to Infra Team for Support
|  | Apply Changes for new Sonar Rules/Any Other Issues | Coforge(Manoj)/IS(Thitipong) | [15 empty] | NA
|  | Configuration Related Verification | Coforge(Manoj) | [15 empty] | Local certificate issue has been resolved, Server issue is also resolved,
|  | Sanity Testing | Coforge(Gaurav)
2 | DB Re-Work | [17 empty] | Delayed - Team has re-sumed activities from 23rd Mar after IS Approval
|  | Conclude Existing Table Re-alignment | Coforge(Manoj)
|  | Discussion with IS & Approval | Coforge(Manoj)/IS(Thitipong)
|  | Take latest table list from prod environment | CoforgeMA(Indranath)
|  | Update mapping list with revised convention for all created stories. | Coforge(Manoj/Dhananjay)
|  | Schema mapping of all tables as per proposed services | Coforge(Manoj/Dhananjay)
|  | Rework on existing table based on impact of DB changes | Coforge(Dhananjay) | [15 empty] | 50 % DB table creation and data loding has been done. 03/29 - We don't have much progress on DB creation part today 03/30 - 80% of table creation and dataloading done 03/31 - DB table creation and data loading done
|  | Rework on existing api based on impact of DB changes | Coforge(Dhananjay) | [15 empty] | 03/30 - Rework for API changes against company code and DB changes is in initial state. We have analyzed and observed that the scope of API changes has increased significantly due to company code implementation. All most every endpoint need to updated. This changes has an impact on complete flow(Cont>Service>Entity>Repository), and similar impact will have at UI side. @Ajay - We still don't have clarity on server side, how we are going to handle this at rework activity to maintain the our existing application up and running, since we have only one environment functional?. 03/31 - Team has started work on API changes against DB changes for admin service. As per discussion company code implementation is not in scope of current changes.
|  | Testing based on the impact areas. | Coforge(Gaurav)
3 | Company Code Design Changes
|  | Detail Under Discussion & Planning | Coforge(Raghu/Peeranut) | [15 empty] | DB design is in progress, Request has been raised with Thitipong to provide the API detail for SC2 authentication information.
4 | UX Finalization | [17 empty] | In-Progress
|  | New Font Changes - Rework | Coforge(Pawan)
|  | Sample UX Changes for Tpex-15/18/19 | Coforge(Pawan)
|  | PO Approval | PO
5 | Common Error Message Re-work | [17 empty] | Backend - 80% message incorporated done, by tomorrow first half will be completed and handover to UI team. 03/29 - Team is still working on changes, significant time was taken by resolving code conflict. 03/30 - Backend part for admin messaging complete and handover to UI team for incorporation at UI end.
|  | Re-work for message changes | Coforge(Pawan/Dhananjay)
6 | Backlog Creation | [17 empty] | Delayed-Target to recover within next week
|  | Story Submission(Required for Sprint-4) | Coforge(Sonu)
|  | BA/PO Review/Closure | Coforge(Sonu)/PO
7 | Refresher KT to Team | [17 empty] | In-Progress
|  | Context Discussion with Team | Coforge(Anshul)
|  | KT Sessions | Coforge(Anshul)